## Sheet1
IT asset | Security risk | Security threat | Vulnerability | Impact of risk | Risk level | Impact level | Existing controls | Proposed controls | Priority | Person responsible | Timeframe for completion | Notes
Network systems | Information involved in electronic messaging gets compromised | Spyware attack | Information in transit is not encrypted. | ● Leakage of sensitive data will attract penalties from regulatory bodies ● Loss of customer trust ● Fall in brand equity | HIGH | HIGH | The security policy states that sensitive data such as passwords are encrypted in SHA256 at rest as well as in transit. | ● Implement encryption for other user sensitive information, such as emails and phone numbers. | HIGH | Dragos-Daniel Bonaparte | 2023-02-22 | N/A
Website | Users are not able to access the website | DDoS attack | The website runs on a free version of the software package, which offers limited security capabilities. | ● Loss of clients due to the inability to provide trust in our service ● Advantage for competitors | MEDIUM | HIGH | None in place. | ● Move the website to a more secure and trusted platform. ● Get SSL certification for the website. | MEDIUM | Dan-Sebastian Ceapa | 2023-06-15 | N/A
Data storage | Records get lost or manipulated due to unencrypted communication channels | Phishing attack | The channel that the data transit occurs is not encrypted. | ● Discrepancies in the records leading to loss of trust from our users. ● Data loss without any backups | HIGH | HIGH | None in place. | ● Develop and implement encryption of channels between all the layers. ● Create a backup database every 7 days. | HIGH | Tomas Gres and Chiril Luncasu | 2023-04-15 | Backup of database done by March 31, 2023.
Firewall | Unauthorized users hack into the system through the internet | Ransomware attack | Company's firewall allows inbound telnet, and guest ID is enabled on XYZ server. | ● Unauthorized access to sensitive files due to system vulnerabilities | HIGH | LOW | None in place. | ● Control the firewall's inbound traffice files. | MEDIUM | Matas Armonaitis | 2022-12-22 | N/A